## Slide 1: V-Cycle Pro Virtual Bike Simulator Project Presentation and Demo by
April 15th , 2010
Lukas-Karim Merhi | CEO
Mike Henrey | Communications/HR
Dan Edmond | Project Manager
Jack Qiao | CFO
Notes: Mike

## Slide 2: Outline
  Background
  Product Design
  High-Level Project Details
  Future Work
  Conclusion
  Acknowledgements
  Questions
Notes: Mike

## Slide 3: Background
Motivation
Current Solutions
Goals
V-Cycle Pro
Background
Notes: Mike

## Slide 4: Vancouver Weather
166 days of rainfall per year in Vancouver
Market already exists – people love to bike
Background – Motivation
Notes: Mike

## Slide 5: Current Solutions
Tacx i-Magic Trainer
Kurt Kinetics Rock and Roll Trainer
Background – Current Solutions
Notes: Mike
- need approx costs, feature breakdown

## Slide 6: Goals and Objectives
Background – Goals
Using your own bike indoors to enjoy a realistic cycling experience | Achieved
Simulated terrain, elevation and resistance. | Achieved
Tilting and turning capabilities | Achieved
Provide user with favourite biking routes | Future work
Notes: Mike
- Should be sexier, maybe rate how we did on each

## Slide 7: Our Solution
Background – V-cycle
Notes: Mike

## Slide 8: Product Design
Overview
Structural
Mechanical
Software
Electronics
Safety
Usability
Sustainability
Product Design
Notes: Transition to Jack

## Slide 9: System Overview
Product Design – Overview
Notes: Jack
- User is central to our system
- Modules to the system, integration a critical step

## Slide 10: Front and Back Platforms
Product Design – Structural
Notes: Jack
Overview of the structural components
Discussion of use of metals for strength, existing trainer etc.

## Slide 11: Front Lifting Mechanism
Linear motion components
Integrated potentiometer
Retains proper bike tire freedoms
Product Design – Mechanical
Notes: Jack
Ballscrew and glides
Discussion of system efficiency etc.

## Slide 12: Tilting Mechanism
Product Design – Mechanical
Notes: Jack
Materials used
Passive system to engage core muscles

## Slide 13: Gravity Assist
Product Design – Mechanical
Notes: Jack
Purpose
Simplicity of design

## Slide 14: Software and Graphical User Interface
Product Design – Software
2 custom virtual terrains | Achieved
Mapping famous, real life routes | Future work
Integration with Google maps/street view | Future work
Notes: Jack
Role visual feedback plays in virtual reality experience
Current and future implementation

## Slide 15: System Overview
Power supply
Microcontroller
Sensors
Motor driver
Product Design – Electronics
Notes: Transition to Dan
- All electronics

## Slide 16: Electronics Systems
Product Design – Electronics
Notes: Dan

## Slide 17: Safety Design
Hard stops constrain linear movements
Limit switches guard linear components
Industrial emergency stop button
Electronics enclosed in grounded box
Fuse protection on power components
Insulated wiring and warning signs
Product Design – Safety

## Slide 18: Versatile Design
Stand Alone Mode (no software)
Active Mode (software interface)
Tilting can be mechanically disabled
Modular Design
  3 main components (back and front platform, control box)
  Set of cables (2 serial, 1 USB, 1 Power)
  Easily disassembled
Product Design – Usability

## Slide 19: Sustainability
Use of recycled materials
  Scrap wood
  Scrap metal
  Left over fasteners
  Old popped bike tubes
  Reused electronic components
Product Design – Sustainability

## Slide 20: High-Level Project Details
Costs
Teamwork
Time Management
Lessons
Future Work
High Level Details
Notes: Lukas
- Teamwork and business aspects

## Slide 21: Project Costs
High Level Details – Costs
 | Realized ($) | Budgeted ($)
Electronics Components | 479.02 | 465.00
Sensors and analog circuitry | 234.02 | 130.00
Digital circuitry | 245.00 | 335.00
Electro-Mechanical Components | 990.88 | 630.00
Structural (Metals, struts, wood, fasteners) | 409.52 | 100.00
Mechanical (Ball screw, linear actuators, motor, power supply, generator) | 376.69 | 380.00
Bike trainer | 204.67 | 150.00
Total | 1469.90 | 1095.00
Notes: Lukas
Outline of the major expenses

## Slide 22: Comments on Costs
Greatly underestimated structural costs
Fried a motor driver
Proposed budget limited purchases of better solutions such as a multi-functional variable resistance unit
Did not qualify for IEEE funding (no wireless components in the design)
High Level Details – Costs
Notes: Lukas
- Discussion of the costs

## Slide 23: Teamwork
 |  | Dan | Mike | Lukas | Jack
Design | Code and circuits | X |  | X | 
 | Structural and mechanical |  | X | X | X
 | Software |  |  |  | X
 | Variable resistance | X | X |  | 
Implement | Computer and MCU | X |  |  | X
 | Structural and mechanical |  | X | X | X
 | Sensors and circuitry | X |  | X | 
High Level Details – Teamwork
Notes: Lukas
How we allocated the work
Teams of people worked on each section

## Slide 24: Development Timeline
High Level Details – Time Management
Item | Proposed | Implemented
Order parts | February 3 | Ongoing
Sensors | February 5 | March 9
Front lift platform | February 19 | April 1
Resistance electronics | February 23 | Not implemented
Tilting system | February 26 | March 1
Stepper code | March 6 | April 14
Resistance mechanical | March 12 | Not implemented
1D acceleration | March 23 | March 22
Notes: Lukas
May have to simplify this if it doesn’t show well on projector
Discussion of proposed vs. actual milestones

## Slide 25: Lessons Learned
Very ambitious project to undertake for a 3 month time period
Not enough mechanical experience at start of project, delayed integration
Proper tools, materials and precise measurements are super essential
Some of us were overloaded with other courses
Group organization should be flexible
High Level Details – Lessons
Notes: Lukas
- Discussion of our take-aways of the project

## Slide 26: Future Work
Multifunctional variable resistance unit
Realistic motion frequencies (i.e. gravel or pavement textures)
Improve gravity compensation system
Hydraulic platform for lifting mechanism
Realistic bike terrain maps
Google street view interfacing
Audible noise reduction
High Level Details – Future Work
Notes: Lukas
- How we see the ideal project

## Slide 27: Excerpts from our Minutes
Oct 1: “Robot skyscraper window washer”
Jan 11: “Side to side tilting not really possible”
Feb 20: “Reed switch, serial Read/Write done… de-bouncing done…”
April 6: “Videos!!!”
Conclusion
Notes: Transition back to Mike
Thank audience for time and interest
Key takeaways for us

## Slide 28: Acknowledgments
Lucky One (electronics advice)
Fred Heep (electronics advice)
Professor Bernhard Riecke (VR advice)
Gianmarco Spiga (Arduino and pie)
Martin Berryman (metalwork assistance)
Brian and Physics Department (machine shop assistance)
Yeelen Merhi (mechanical design inspiration)
Rest of the Hewitt House (Audrey-Anne, Pier Alexandre, Sean Edmond)
ESSS (for ESSEF funding grant allocation and distribution)
Acknowledgements
Notes: Mike

## Slide 29: Questions?
Questions
Notes: Mike

## Slide 30
Please join us in the pub after the demonstration…